## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
0u4NDk8QPU6mtqTts47ZRWQAC6-G | Meeting 3 - all | Review & Planning | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 12/01/2025 | 12/01/2025 | 12/01/2025 | false | false | 12/03/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Software analysis
DDA2tLHSwEK_AlH5xdU6XWQAAa9a | Online Submission (Email) | Finalization & Submission | Completed | Important | Francis Oladimeji Ajibade | Chukwuemeka Benedict Anyanwu | 11/28/2025 |  | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | The online submission comprises of sending the professor an email with the project GitHub link.
EUI19i3dMkyezNWfEgKYCGQAPWkb | Meeting 5 - all | Review & Planning | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 12/08/2025 | 12/08/2025 | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Finalizing all elements of the project submission and test scenarios.
G6F3-EIUTkK-dfGXky8MemQAELJj | Project Branches | Setup & Initialization | Completed | Medium | Chukwuemeka Benedict Anyanwu;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/03/2025 | 12/05/2025 | false | false | 12/04/2025 | Tamunotonye Jackreece |  |  |  | Creation of the new branches to allow commits from each member as we work on various sections of the submission.
GXLqT2jhgkK_u4NoggDe4GQAH5SW | Review Professor Email(s) - all | Review & Planning | Completed | Urgent | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 11/28/2025 | 11/28/2025 | false | false | 12/04/2025 | Tamunotonye Jackreece | 3/3 | Compare professor's statements to our previous submission, to identify key areas of focus;Read professor's comments, warnings and feedbacks;Discuss and come up with potential resolutions. |  | Jose Tasse sent emails with additional feedbacks and comments regarding the submission 3 which needs to be discussed as the changes would be observed in submission 4.
M9P_APfLtkiJAMacyFY5dGQADvLo | Meeting 4 - all | Review & Planning | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 12/03/2025 | 12/07/2025 | 12/08/2025 | false | false | 12/08/2025 | Chukwuemeka Benedict Anyanwu
OIr-SxlE3USNpC5IJlw6KmQAFmBZ | In-person submission (Printing) | Finalization & Submission | Completed | Important | Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 11/28/2025 |  | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | This submission comprises of a printable copy of the description of necessary modifications to the requirements, diagrams (class & Sequence), and the MS Planner document.
PG4yk_uF20GOLwygSzSYkmQADrcf | Requirement Changes Space | Setup & Initialization | Completed | Medium | Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 11/28/2025 |  | 11/29/2025 | false | false | 12/04/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | The document for recording modifications done on the project requirements
PKuseFjo4Ua4CWt5idbpCWQAPutU | Implementing Result Comparisms | Production & Implementation | Completed | Medium | Francis Oladimeji Ajibade;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 12/08/2025 |  | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu
Sf3fg6AQlEaMA-i9OMRuKGQAPSE_ | FR & NFR Changes - all | Requirement Modifications & Changes | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 |  | 12/01/2025 | false | false | 12/03/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Discussion and listing of the functional and non-functional requirement changes
WPKpB8BDUk6dVy-jndhZamQAADha | Scenario Prep | Finalization & Submission | Completed | Important | Tamunotonye Jackreece;Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/06/2025 | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu | 3/3 | Allow the professor to test all the new modifications;Guide the professor across all parts of the software.;Allow the professor to test all the previous features |  | Prepare a test case scenario to guide the professor on how to test our software. The scenario must cover the her requirements (inside checklist).
ZvEZ51RbTkW9GzbI08qiMmQAIRxI | Sequence Diagram Changes | Requirement Modifications & Changes | Completed | Medium | Francis Oladimeji Ajibade;Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/03/2025 | 12/04/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Updates to all of our sequence diagrams to reflect changes in the requirements and use cases.
g2Dwzu7xNk2s_n62ChmeTWQAIMfN | Meeting 1 - all | Review & Planning | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 11/28/2025 | 11/28/2025 | false | false | 12/01/2025 | Chukwuemeka Benedict Anyanwu | 3/3 | Team attendance;Review Submission 4 Checklist;Review submission 3 Feedback |  | First group meeting. Reviewing Submission 3 feedback and Submission 4 requirements.
h_V0vswbRE6ZRDDz0644GmQAC80r | Implementing Save Test Suite Result Functionality | Production & Implementation | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/08/2025 |  | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu
j5F3tprEr0S3GE6Qb8ymemQALQSE | GitHub Contributors | Setup & Initialization | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/03/2025 | 12/05/2025 | false | false | 12/04/2025 | Chukwuemeka Benedict Anyanwu | 0/3 | Ensure that each team member's GitHub corresponds to team member id;Check that all team members are added as contributors;Add any team member missing and ensure they have appropriate permissions |  | Ensure all members of the team have been added as contributors to the GitHub repository.
jDjXkBvbfkONEtk_iypmOGQAMNem | Team Task Management | Setup & Initialization | Completed | Medium | Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 12/03/2025 | 11/28/2025 | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Managing all related planner activities from creation, assigning, coordination & updating of tasks across the submission.
jbDBgHjT406VHk7-MDVGuWQAP6zh | Local Setup & Configuration - all | Setup & Initialization | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 11/28/2025 | 11/30/2025 | false | false | 12/01/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Making sure all team members can access and commit to the GitHub repository from their respective devices.
nZuaFpD5EkO0FzblKaBbQWQAMttx | Class Diagram Changes | Requirement Modifications & Changes | Completed | Medium | Francis Oladimeji Ajibade;Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/03/2025 | 12/04/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Updating the final class diagram to add/modify/remove classes to reflect the new requirements
pEa1cGHxNUq1VEZrBSwxK2QADAn7 | Implementing Load Suite Result Functionality | Production & Implementation | Completed | Medium | Chukwuemeka Benedict Anyanwu;Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 12/08/2025 |  | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu
q3YWiH1ZbUuTOkq-xFj62GQAJY7A | Meeting 2 - all | Review & Planning | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 11/29/2025 | 11/29/2025 | false | false | 12/01/2025 | Chukwuemeka Benedict Anyanwu | 4/4 | Submission 4 task break down;Revisit our submission 3 work;Discuss Submission 4 requirements;Attendance |  | Team revision of our submissions 3 work, brainstorming and work breakdown.
swXw8f1S4UO_vGfbTpxi72QAH3v3 | Final Requirement List Upload | Production & Implementation | Completed | Medium | Vikramjit Singh | Chukwuemeka Benedict Anyanwu | 12/03/2025 | 12/03/2025 | 12/04/2025 | false | false | 12/04/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Committing the final document to our GitHub repository.
wUoIAc5TFECfAM02QU0u0WQAMayI | Final Requirements Review - all | Production & Implementation | Completed | Medium | Francis Oladimeji Ajibade;Chukwuemeka Benedict Anyanwu;Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 12/03/2025 | 12/02/2025 | 12/04/2025 | false | false | 12/04/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Final Overall Review of the Updated Requirements list
xJdK1ETBp0GQiWHZROsauGQABi_i | Visual Paradigm Space | Setup & Initialization | Completed | Medium | Chukwuemeka Benedict Anyanwu | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 11/28/2025 | 11/29/2025 | false | false | 12/01/2025 | Chukwuemeka Benedict Anyanwu |  |  |  | Creating the project space for the updated changes to our project diagrams (class diagram, sequence diagrams).
yu3ys7lJgkGUb2oOvyu-DWQAOCQ4 | Documents Compilation | Finalization & Submission | Completed | Medium | Vikramjit Singh;Tamunotonye Jackreece | Chukwuemeka Benedict Anyanwu | 11/28/2025 | 12/08/2025 | 12/09/2025 | false | false | 12/09/2025 | Chukwuemeka Benedict Anyanwu | 2/2 | Compile all the files; code, plans, diagrams, etc.;Ensure all files are not broken and accessible |  | Compilation of all files and documents for submission.

## Plan name
Plan name | CS 2043 - Subm 4 - Group 12
Plan ID | D4Njk0L3fUux4Fnt5L1zUGQAGMp7
Date of export | 12/09/2025